{"text_format":"3","workbook":"xls","n_sheets":10,"sheets":["附表1森林小镇建设","附表2“三旧”改造增绿","附表3交通干线生态廊道","附表4滨水河道生态廊道","附表5城市空间立体绿化","附表6退耕还林建设","附表7限桉退桉提质工程","附表8千亩绿心群建设工程","附表9公园建设项目","附表10村（居）公园建设项目"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"附表1森林小镇建设","index":0,"n_rows":7,"n_cols":11,"rows_kept":7,"merged":[[0,0,0,1],[1,0,1,10],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,2,7],[2,8,2,10]],"flags":["formulas_cached_only"]}
["附件2-1    "]
["                                             森林小镇建设工程项目"]
["序号","拟建森林小镇的镇（街）名称","启动时间","计划完成时间","投资总额（万元）","建设进度",null,null,"项目责任单位（责任人）"]
[{"$nulls":5},2018,2019,2020,"责任单位","负责人","项目联络人及联系电话"]
[1,"杨和镇森林小镇","2018年","2020年",10000,"制订工作方案，编制建设规划，建立项目库，并启动一批建设项目。","根据森林小镇指标评价体系，全力推进并完成各林业绿化项目，力争各项指标基本达到标准。","查漏补缺，进一步完善提升短板指标，8月份前完成申报森林小镇，并顺利通过验收。","杨和镇","朱立坚","林庆泉\n13925951928"]
[2,"更合镇森林小镇","2018年","2020年",2500,"制订工作方案，编制建设规划，建立项目库，并启动一批建设项目。","根据森林小镇指标评价体系，全力推进并完成各林业绿化项目，力争各项指标基本达到标准。","查漏补缺，进一步完善提升短板指标，8月份前完成申报森林小镇，并顺利通过验收。","更合镇","潘海洋","谭剑雄88842028"]
[3,"明城镇森林小镇","2016年","2020年",2660.8,"巩固期主要对前期的建设成果进行维护与保持巩固，同时适当增加绿地与林地，提升整体环境","巩固期主要对前期的建设成果进行维护与保持巩固，同时适当增加绿地与林地，提升整体环境","提升期旨在对明城镇休闲游憩环境进行全面提升，使明城镇生活环境由持续扩绿造林的量变达到“宜居”、“宜养”、“宜游”的质变。","明城镇","陈伟光","区有雄88831202"]

{"sheet":"附表2“三旧”改造增绿","index":1,"n_rows":6,"n_cols":11,"rows_kept":6,"merged":[[0,0,0,1],[1,0,1,10],[5,1,5,3]],"flags":["formulas_cached_only"]}
["附件2-2 "]
["“三旧”改造增绿工程项目"]
["序号","项目名称","项目位置","主要建设内容","新增绿地面积（公顷）","用地情况及用地解决方案","总投资           （万元）","出资方式","开工、完工时间","责任单位","备注"]
[1,"三洲旧区改造","碧桂路以东、滨河路和三洲旧桥以南、沧江南路以北及沧江桥和高明河堤以西组成区域","三洲旧区改造控制性详细规划范围内的所有改造工作（包括区域内征地拆迁、安置房建设、市政基础设施建设、土地整理）。",5.98,"符合用地手续和利用总体规划",3622.19,"社会融资","2018.1月、2020.6月","区国土城建和水务局（国土）、荷城街道办","区国土城建和水务局（国土）作为行业统筹单位，荷城街道办作为项目实施单位。"]
[2,"高明沿江路以东（荷城公园至灵龟公园段）旧城改造项目","荷城街道","本项目为打造高明江滩滨河景观工程河漫滩（荷城公园至灵龟公园段）区域内的生态湿地公园，包括沙滩休闲区、花田远动区、湿地亲水区等功能区域内的景观、绿化工程建设，建设面积约168亩。",11.2,"建设用地已落实，该项目已基本完成。",3392.32,"社会融资","2017.8月、2018.2月","区国土城建和水务局（国土、重建代建）","区国土城建和水务局（国土）作为行业统筹单位，区国土城建和水务局（重建代建）作为项目实施单位。"]
["项目小计","高明区2个项目",null,null,17.18,null,7014.51]

{"sheet":"附表3交通干线生态廊道","index":2,"n_rows":22,"n_cols":11,"rows_kept":22,"merged":[[0,0,0,1],[1,0,1,10],[21,1,21,3]],"flags":["formulas_cached_only"]}
["附件2-3"]
["交通干线生态廊道工程项目"]
["序号","项目名称","项目位置","主要建设内容","新增绿地面积（公顷）","新增绿化长度（米）","总投资（万元）","出资方式","开工、完工时间","责任单位","备注"]
[1,"明西路扩建工程","荷城、杨和","一级公路标准双向六车道主路，全长7.182公里",{"v":1.4364,"d":"1.44"},7182,1081,"地方政府自筹","2018.9.30日、2021年","区交通运输城管局（交通）"]
[2,"X498明富线明城至河村段改建工程","荷城、明城","一级公路标准双向六车道主路，全长10.7公里",2.14,10700,449,"地方政府自筹","2018-9-30日、2021年","区交通运输城管局（交通）"]
[3,"荷杨大道茶山公路及杨西立交工程公路","荷城、杨和","一级公路标准双向四至六车道",1.43,7174,454,"合作建设","2015.9.30日、2019年","区交通运输城管局（交通）"]
[4,"高明区石岐路道路及配套设施工程、高明区石岐路道路及配套设施工程","荷城街道","按城市次干道标准建设，长1.089公里",0.33,1089,145,"地方政府自筹","2018-9-30日、2020年","区交通运输城管局（交通）"]
[5,"高明区海华桥及其引道工程","荷城街道","一级公路标准兼顾城市道路功能，长1.463公里",{"v":0.1294,"d":"0.13"},792,460,"地方政府自筹","2018-9-30日、2021年","区交通运输城管局（交通）"]
[6,"高明区九公里林场2018年\n景观林带建设、高明区九公里林场2018年\n景观林带建设","九公里林场杨宅线","为提升高明区九公里林场景观及生态公益林的林分质量，提高生态林的等级，提升高明区旅游竞争力，在九公里林场权属范围内实施150亩桉树纯林林分改造及450亩杨宅线九公里林场内长约3公里的路段两侧景观改造（分为道路至防火林带区域180亩，防火林带至山体延伸区域270亩）。",{"v":40,"d":"40.00"},"改造提升长度3000米",345,"财政投资","2018年、2019年","杨和镇"]
[7,"怡乐路（荷富路至凤凰路段）","西江新城","路线全长555m，建设内容包括道路工程、排水工程、交通工程、交通信号灯工程、照明工程、绿化工程",{"v":1,"d":"1.00"},"555米（分中间绿化带及道路两边绿化带）",3300,"银行贷款","2017.11月、2019.12月","西江新城"]
[8,"怡乐路（泰华路至祥福路段）","西江新城河江村","路线全长550m，建设内容包括道路工程、排水工程、交通工程、交通信号灯工程、照明工程、绿化工程",{"v":1,"d":"1.00"},"555米（分中间绿化带及道路两边绿化带）",5051,"银行贷款","2018.3月、2019.12月","西江新城"]
[9,"荷富大道（罗西片区）西侧辅道","高明区荷富大道（跃华路至明国路）西侧","本工程为荷富大道（罗西片区）西侧辅道工程，路线起于跃华路交叉口，终于公路局路口，路线全长1.2km，建设内容包括道路工程、排水工程、交通工程、交通信号灯工程、照明工程、绿化工程",{"v":2,"d":"2.00"},"单侧绿化带1.2km",1672,"银行贷款","2017.3月、2018.6月","西江新城"]
[10,"一环西拓南环高明杨西大道北延线段工程","明城、荷城","一级公路标准双向六车道主路，长9.02公里",{"v":1.804,"d":"1.80"},9020,669,"政府采购服务","2017-6-30日、2019-12-30日","区交通运输城管局（交通）"]
[11,"一环西拓南环高明富湾富龙特大桥工程","荷城街道","一级公路标准双向八车道主桥，荷富以西段引道双向六车道主路，全长5.2公里",{"v":0.334,"d":"0.33"},1670,2075,"PPP模式","2018-4-30日、2020-12-30","区交通运输城管局（交通）"]
[12,"荷香路北延伸道路建设工程（跃华路～怡乐路段）","荷城街道","城市主干路，长0.9公里",0.36,900,136,"PPP模式","2016-5-3日、2018年","区交通运输城管局（交通）"]
[13,"高恩高速公路（高明段）工程建设","更合镇","本项目主要建设高速公路，高明至恩平高速公路佛山高明段，全线长约5.768公里，征地总面积约771.647亩（包括补征地（改路、改沟）用地）",5.77,5768,"待定","待定","2016-10-1日、2018年底","区交通运输城管局（交通）"]
[14,"2018年高明区明城镇明富路(明城至平山一路段)改建工程","明城镇","采用一级公路技术标准，路线途经高田村、桥头村、江边村、红岗村，终点与平山一路交接，设计速度为60km/h，设双向四车道，采用沥青混凝土路面结构。",{"v":1.6,"d":"1.60"},8000,20000,"PPP模式","2018.11月、2020.12月","明城镇"]
[15,"平山路（河南新城区路段）提升改造工程","明城镇","为了进一步加快明城河南新城区的开发建设，我镇拟动工兴建平山路（河南新城区路段）的道路及辅道和排水设施等工程。该路段长约3公里，设双向六车道和辅道。",{"v":0.6,"d":"0.60"},3000,30000,"社会融资","2018年、2020年","明城镇"]
[16,"Y011旧沧江桥至合和大道路面扩宽工程","明城镇","路线总长3公里，由原来两车道扩宽至四车道。",{"v":0.6,"d":"0.60"},3000,10000,"社会融资","2018年、2020年","明城镇"]
[17,"高明大道辅道及行人道建设工程","明城镇","在原有状况增加排水、绿化，并增加辅道和人行道，路线总长约10公里。",{"v":5,"d":"5.00"},10000,12000,"社会融资","2018年、2020年","明城镇"]
[18,"高明区全域旅游基础设施工程—城市门户","广明高速荷城出口、沧江出口，以及江肇高速杨和出口","高速出入口景观改造",{"v":32,"d":"32.00"},"——",9000,"财政资金","2018.09—2019.09","区文化体育局"]
["项目小计","高明区共18项",null,null,{"v":97.53380000000001,"d":"97.53"},68295,96837]

{"sheet":"附表4滨水河道生态廊道","index":3,"n_rows":9,"n_cols":12,"rows_kept":9,"merged":[[0,0,0,1],[1,0,1,11],[8,1,8,3]],"flags":["formulas_cached_only"]}
["附件2-4"]
["滨水河道生态廊道工程项目"]
["序号","项目名称","项目位置","主要建设内容","新增绿地面积（公顷）","新增绿化长度（米）","用地情况及用地解决方案","总投资（万元）","出资方式","开工、完工时间","责任单位","备注"]
[1,"秀丽河堤围综合整治工程（西江大道至跃华路段）景观工程东岸I标段","西江新城","沿河滩地进行绿化提升工程，园建工程、排水工程等",3.65,3.65,"已落实",1550,"财政资金","2016.6月、2018.2月","西江新城"]
[2,"秀丽河堤围综合整治工程（西江大道至跃华路段）景观工程东岸Ⅱ标段","秀丽河东岸西江大道至跃华路段","沿河滩地进行绿化提升工程，园建工程、排水工程等",6.67,1000,"已完成土地征收工作",3500,"银行贷款","2018.1月、2019.12月","西江新城"]
[3,"秀丽河堤围综合整治工程（明湖北路至秀丽路）景观工程（东岸段）","秀丽河东岸明湖北路至秀丽路段","沿河堤围进行绿化景观提升工程，园建工程、排水工程等","10（按规划面积）",1500,"已完成部分土地征收工作",8000,"银行贷款","2020年1月，2022年12月","西江新城"]
[4,"高明区围拳涌黑臭水体整治工程（荷富大道—大德路段）","围拳涌（大德路ˉ荷富大道）","河涌整治工程（包括路面工程、排水工程、绿化工程、交通工程、补水工程等）",0.3,400,"已完成土地征收工作",1785,"财政资金","2017.2月、2019.12月","区土建水务局（水务）"]
[5,"高明区全域旅游基础设施工程—杨梅河（北段）","杨梅河（北段）","沿河两岸景观改造提升","——","——","本项目不需新增建设用地。沿河两岸的改造使用两岸边上的绿地进行景观改造；绿道为6米以下道路；",20000,"财政资金","2019.9月、2021.9月","区文化体育局","围绕杨梅河水系的生态景观，结合水系肌理条件，建设差异化功能的绿道系统，向外部延伸并串联林地、湿地、田园、古村、度假区、景区等其他自然空间与人文环境。数据以最终审核通过的可研报告为准。"]
["项目小计","高明区共5个项目",null,null,20.62,2903.65,null,34835]

{"sheet":"附表5城市空间立体绿化","index":4,"n_rows":6,"n_cols":13,"rows_kept":6,"merged":[[0,0,0,1],[1,0,1,12],[5,1,5,3]],"flags":["formulas_cached_only"]}
["附件2-5"]
["城市空间立体绿化工程项目"]
["序号"," 项目名称","项目位置","主要建设内容","新增绿地面积（公顷）","新增绿化长度（米）","用地情况及用地解决方案","总投资（万元）","出资方式","开工时间","完工时间","责任单位","备注"]
[1,"明城镇城五路跨沧江河桥","明城镇","城五路与沧江河交界处，是连接现明城中心城区和河南新城区的南北向重要交通干道。为了改善我镇南部的交通条件，加强明城中心城区和河南新城区的连接，促进我镇南部的经济法杖。该桥主桥长150米，南北两侧引桥各长200米，桥宽40米。",0.11,550,"符合土规",6500,"社会融资",2018,2019,"明城镇"]
[2,"明城镇城七路跨沧江河桥","明城镇","城七路与沧江河交界处，是连接现明城中心城区和河南新城区的南北向重要交通干道。为了改善我镇南部的交通条件，加强明城中心城区和河南新城区的连接，促进我镇南部的经济法杖。该桥主桥长150米，南北两侧引桥各长200米，桥宽40米。",0.11,550,"符合土规",6500,"社会融资",2018,2019,"明城镇"]
["项目小计","高明区共2项",null,null,0.22,null,null,13000]

{"sheet":"附表6退耕还林建设","index":5,"n_rows":7,"n_cols":11,"rows_kept":7,"merged":[[0,0,0,1],[1,0,1,10],[3,10,5,10],[6,1,6,3]],"flags":["formulas_cached_only"]}
["附件2-6"]
["退耕还林建设工程项目"]
["序号"," 项目名称","项目位置","小班号","面积（公顷）","总投资（万元）","出资方式","开工时间","完工时间","责任单位","备注"]
[1,"退耕还林","杨和镇","/",66.96,210,"社会投资",2018,"2020年","杨和镇","区国土城建和水务局（国土）作为行业统筹单位，各镇作为项目实施单位。"]
[2,"退耕还林","明城镇","/",22.54,67.62,"财政出资",2018,2020,"明城镇"]
[3,"退耕还林","更合镇","/",61.62,185,"财政投资",2018,2020,"更合镇"]
["项目小计","高明区共3项",null,null,151.12,462.62]

{"sheet":"附表7限桉退桉提质工程","index":6,"n_rows":13,"n_cols":11,"rows_kept":13,"merged":[[0,0,0,1],[1,0,1,10],[12,1,12,3]],"flags":["formulas_cached_only"]}
["附件2-7"]
["限桉退桉提质工程项目"]
["序号"," 项目名称","项目位置","小班号","面积（公顷）","总投资（万元）","出资方式","开工时间","完工时间","责任单位","备注"]
[1,"荷城街道2018年-2020年森林碳汇重点生态工程","荷城街道","以实际调查为准",400,1266,"财政投资",2018,2022,"荷城街道"]
[2,"杨和镇2018年-2020年森林碳汇重点生态工程","杨和镇","以实际调查为准",400,1266,"财政投资",2018,2022,"杨和镇"]
[3,"明城镇2018年-2020年森林碳汇重点生态工程","明城镇","以实际调查为准",400,1266,"财政投资",2018,2022,"明城镇"]
[4,"更合镇2018年-2020年森林碳汇重点生态工程","更合镇","以实际调查为准",400,1266,"财政投资",2018,2022,"更合镇"]
[5,"区林科所2018年-2020年森林碳汇重点生态工程","区林科所","以实际调查为准",164,519.06,"财政投资",2018,2022,"区林科所"]
[6,"荷城街道2018-2022年限桉退桉工程","荷城街道","以实际调查为准",113,357.65,"社会投资",2018,2022,"荷城街道"]
[7,"杨和镇2018-2022年限桉退桉工程","杨和镇","以实际调查为准",943,84.87,"社会投资",2018,2022,"杨和镇"]
[8,"明城镇2018-2022年限桉退桉工程","明城镇","以实际调查为准",858,2574,"社会投资",2018,2022,"明城镇"]
[9,"更合镇2018-2022年限桉退桉工程","更合镇","以实际调查为准",3077,9738.7,"社会投资",2018,2022,"更合镇"]
["项目小计","高明区共9项",null,null,6755,18338.28]

{"sheet":"附表8千亩绿心群建设工程","index":7,"n_rows":5,"n_cols":12,"rows_kept":5,"merged":[[0,0,0,1],[1,0,1,11],[4,1,4,3]],"flags":["formulas_cached_only"]}
["附件2-8"]
["千亩绿心群建设工程项目"]
["序号","项目名称","项目位置","主要建设内容","新增绿地面积（公顷）","用地情况及用地解决方案","总投资（万元）","出资方式","开工时间","完工时间","责任单位","备注"]
[1,"西江新城山水走廊","西江新城","西江新城山水走廊主要串联智湖湿地公园、明湖湿地公园、南蓬山森林公园。（1）智湖湿地公园位于广东省佛山市高明中心城区西北部，秀丽河的北端，西部靠近古椰村，东部与君御海城相邻，公园用地范围主要包括沿秀丽河河岸的河漫滩及部分秀丽河水域，湿地率 44.99%。（2）明湖湿地公园位于广东省佛山市高明区西江新城核心区荷富路旁，四至范围北起府前路，南至滨湖路，西临荷富路，东及苏河路，总面积 240亩，湿地率 44.08%。（3）南蓬山森林公园位于高明城区东北部，西北距富湾圩3.5 公里，东起西江江岸的沿江路，西与S362 公路相邻，北起大田，南止官棠，森林覆盖率达到90%","根据项目实际增加","二期项目用地待落实"," ","财政资金","2018年","2020年","西江新城","西江新城山水走廊主要串联智湖、明湖以及南蓬山，西江新城智湖公园、明湖公园一期已经完工并投入使用，智湖投资总额约为8327.92万元，明湖一期总投资约1.7亿元。明湖二期列入核心区二期项目内，由于核心区二期因未能明确开发模式及适合西江新城发展的产业定位，对方案的编制存在一定的不明朗因素，同时由于二期工程用地未解决，导致二期项目进展未如期。"]
["项目小计","高明区共1项",null,null,"待定"]

{"sheet":"附表9公园建设项目","index":8,"n_rows":30,"n_cols":14,"rows_kept":30,"merged":[[0,0,0,1],[1,0,1,13],[3,0,7,0],[8,0,19,0],[11,13,12,13],[21,0,28,0],[29,1,29,4]],"flags":["formulas_cached_only"]}
["附件2"]
["公园建设项目"]
["类别","序号","项目名称","项目位置","主要建设内容","公园面积（公顷）","新增绿地面积（公顷）","用地情况及用地解决方案","总投资（万元）","出资方式","开工时间","完工时间","责任单位","备注"]
["湿地公园",1,"白鹭湖湿地公园","杨和镇","待定",58.45,50.26,"待定",38000,"待定",2018,2020,"杨和镇"]
[null,2,"更合镇蛇塘村湿地公园","更合镇蛇塘村内","建设亲水设施，种植亲水植物",2.38,2.38,"待定",120,"待定","计划2019年动工","2020年","更合镇","现处于用地调查中"]
[null,3,"更合镇荔枝园湿地公园","更合镇白石村委会荔枝园村内","建设亲水设施，种植亲水植物",17.91,17.91,"待定",150,"待定","计划2020年动工","2021年","更合镇","现处于用地调查中"]
[null,4,"更合镇松围村村后湿地公园","更合镇宅布村委会松围村","建设亲水设施，种植亲水植物",5,5,"待定",120,"待定","计划2021年动工","2022年","更合镇","现处于用地调查中"]
[null,5,"渔港河湿地公园","明城镇","待定",10,10,"待定","待定","财政出资",2018,"待定","明城镇"]
["镇级公园",1,"杨和镇镇级公园","杨和镇政府旁","新建公园绿地",1.5,1.5,"在规划绿化用地上建设",70,"财政出资",2017,2018,"杨和镇"]
[null,2,"明湖公园二期","西江新城明湖北路以南，大德北路以北，荷富路以西，秀丽河以东","约 800亩水体及相关绿化等配套配套基础设施。",11,11,"正在进行土地征收工作",16000,"PPP","计划2018年","2022-12-01","西江新城"]
[null,3,"更合镇白石公园景观改造工程","更合大道原碧丽山庄内","对原址进行改造，改造面积约25亩，包括园建、排水、电气、绿化工程",1.67,1.67,"符合用地要求",137.5,"财政投资",2016,2017,"更合镇"]
[null,4,"高明更合镇贝拉角森林旅游度假区","更合镇界村村","打造成一座凝聚意大利艺术精华，集农业体验、观光休闲、养生度假、旅游接待酒店等功能于一体的生态休闲度假区",260,260,"1、缺乏用地规模，项目用地未能纳入中期调整；                         2、项目缺乏城乡建设用地指标；                         3、项目有35公顷需要进行林地变更，但林地变更难度大。",50000,"社会融资",2020,2022,"更合镇"]
[null,5,"东方山地休闲乐活谷","更合镇大幕村","项目拟规划打造一个以养生文化、生态文化、艺术文化、康体文化、商务度假为一体的多元化，高起点的国际休闲生态乐活社区",83.3,40,"1、缺乏用地规模，项目用地未能纳入中期调整；                2、项目缺乏城乡建设用地指标600亩（已有50亩交资料审批）；                             3、项目有71.78公顷需要进行林地变更，但林地变更难度大",50000,"社会融资",2020,2022,"更合镇"]
[null,6,"滨河运动公园设施","东洲鹿鸣体育小镇","充分利用鹿鸣湖大水面及沧江河道，设置多样化的水上极限与运动休闲基地。",1.2,0.43,"待定",5000,"待定",2018,2020,"明城镇"]
[null,7,"街头极限运动公园","东洲鹿鸣体育小镇","打造珠三角街头极限运动第一大本营",1.2,0.43,"待定",12000,"待定",2018,2021,"明城镇"]
[null,8,"明阳山户外运动公园","东洲鹿鸣体育小镇","利用明阳山地形，面向大众游客开展多种户外活动项目",1.2,0.43,"待定",5000,"待定",2018,2020,"明城镇"]
[null,9,"华山公园","公正路以北、大新路以南","华山公园提升改造",0.7735,0.7735,"符合用地手续和利用总体规划","正正进行前期立项工作，未有投资预算",null,"未确定动工时间",null,"三洲旧区改造办、环运分局（市政）"]
[null,10,"接源街改造项目","更合镇更楼更楼工业大道旁","绿化公园",0.47,0.47,"项目内解决",51,"社会融资",2019,2020,"更合镇"]
[null,11,"佛山市高明区欧浦置业投资有限公司欧浦花城项目","佛山市高明区杨和镇杨西大道133号","相关绿化等配套配套基础设施。","/",4.5,"一期绿化已完工，二期绿化在规划设计中。",1200,"社会融资","2018-01-01","2020-12-01","杨和镇"]
[null,12,"云山诗意花园项目","杨和镇大道中47号","相关绿化等配套配套基础设施。","/",1.4,"计划2018年开工，目前正在规划设计中。",600,"社会融资","2018-01-01","2020-12-01","杨和镇"]
["农业公园",1,"鹭湖明珠生态农业观光项目","杨和镇大沙水库南边","规划建设观光农业园、会所、水乐园、探险乐园、暮光森林、天空之城、小羊牧场、欧洲村、每月居、花之谷、金花茶、茶花种植区，另外包括道路、停车场等配套设施。",80,80,"待定",30000,"社会融资",2016,2023,"杨和镇"]
["其他类型生态公园",1,"佛山市高明区泰康山生态旅游度假区项目","明城镇城十路石塘段泰康山生态度旅游度假区","总规划占地面积4276亩，园区建设有十五公里的环山路、酒楼、30亩的钓鱼场、9公里水上游船、登山径及农业生态项目、空中楼阁别墅、养生酒店、金花茶园。",286.492,1.01,"待土地指标落实;将部分生态公益林调整为经济林",120000,"企业自筹",2008,2020,"明城镇"]
[null,2,"国家4A旅游景区佛山市皂幕山旅游风景区","杨和镇石水村委会坑美林场","将皂幕山景区打造成国家5A景区，建设皂幕山·运动森林度假集群。对道路两侧景观进行梳理，保留现状高大乔木，清除杂乱无章的灌木与地被，对现状林前侧空间进行种植提升",1640.29,{"v":10,"d":"10.00"},"待定",36000,"社会融资",2012,2025,"杨和镇"]
[null,3,"郁金香主题公园","明城镇","打造一个1200亩的郁金香主题公园",80,80,"待定",12000,"社会融资","2017年","待定","明城镇"]
[null,4,"南蓬山森林公园","佛山市高明区富湾镇","进行山上林相改造，山下建设公园广场",21.2,21.2,"已落实",1700,"财政投资",2016.9,2018.3,"区国土城建和水务局（重建代建）"]
[null,5,"高明区全域旅游基础设施工程—皂幕山外围环境改造","杨和镇皂幕山","皂幕山外围环境改造",16.35,"/","符合土规",9000,"财政资金",2019.09,2020.09,"区文化体育局"]
[null,6,"鹿洞山森林公园林分改造项目","林科所鹿洞山场部","进行林分改造",1137.5,94.68,"已落实",270,"财政投资","其中729亩林分改造开工时间是2017年3月，691.2亩预计开工时间是2019年1月。","其中729亩林分改造计划竣工时间是2019年12月，691.2亩预计竣工时间是2021年12月。","区林业科学研究所"]
[null,7,"皂幕山森林公园林分改造项目","林科所皂幕山场部","进行林分改造",477.2,5.68,"已落实",18,"财政投资","2019-01-01","2021-12-01","区林业科学研究所"]
[null,8,"珍稀名贵树种种植示范基地","林科所本场部","进行林分改造",182.8,68.56,"已落实",213,"财政投资","其中237亩林地已于2016年11月开工，其余林地预计2019年开工","其中237亩计划竣工时间是2019年12月，其余林地预计竣工时间是2021年12月","区林业科学研究所"]
["项目小计","高明区共26个项目",{"$nulls":3},{"v":4377.8855,"d":"4377.89"},{"v":769.2835000000002,"d":"769.2835"},null,{"v":387649.5,"d":"387649.50"}]

{"sheet":"附表10村（居）公园建设项目","index":9,"n_rows":77,"n_cols":14,"rows_kept":77,"merged":[[0,0,0,1],[1,1,1,13],[3,0,74,0],[76,2,76,4]],"flags":["formulas_cached_only"]}
["附件2-10"]
[null,"村（居）公园建设项目"]
["序号1","序号2","项目名称","项目位置","主要建设内容","公园面积（公顷）","新增绿地面积（公顷）","用地情况及用地解决方案","总投资（万元）","出资方式","开工时间","完工时间","责任单位","备注"]
["1.村居公园",1,"白洞“五好”新村居建设绿化提升项目工程","更合镇白洞村委会","休闲公园",0.2,0.13,"村集体地",25,"社会融资",2018.1,2018.3,"更合镇"]
[null,2,"水井“五好”新村居建设绿化提升项目工程","更合镇水井村委会","休闲公园",0.13,0.1,"村集体地",13,"社会融资","2018.1","2018.3","更合镇"]
[null,3,"香山“五好”新村居建设绿化提升项目工程","更合镇香山村委会","休闲公园",0.1,0.03,"村集体地",10,"社会融资","2018.1","2018.3","更合镇"]
[null,4,"巨泉“五好”新村居建设绿化提升项目工程","更合镇巨泉村委会","休闲公园",0.27,0.18,"村集体地",48,"社会融资","2018.1","2018.3","更合镇"]
[null,5,"宅布“五好”新村居建设绿化提升项目工程","更合镇宅布村委会","休闲公园",0.07,0.04,"村集体地",12,"社会融资","2018.1","2018.3","更合镇"]
[null,6,"泽河“五好”新村居建设绿化提升项目工程","更合镇泽河村委会","休闲公园",0.17,0.1,"村集体地",20,"社会融资","2018.1","2018.3","更合镇"]
[null,7,"大幕“五好”新村居建设绿化提升项目工程","更合镇大幕村委会","休闲公园",0.1,0.04,"村集体地",10,"社会融资","2018.1","2018.3","更合镇"]
[null,8,"新圩“五好”新村居建设绿化提升项目工程","更合镇新圩居委会","休闲公园",0.12,0.04,"村集体地",10,"社会融资","2018.1","2018.3","更合镇"]
[null,9,"更居“五好”新村居建设绿化提升项目工程","更合镇更楼居委会","休闲公园",0.08,0.04,"村集体地",10,"社会融资","2019","2019","更合镇"]
[null,10,"珠塘“五好”新村居建设绿化提升项目工程","更合镇珠塘村委会","休闲公园",0.7,0.3,"村集体地",8,"社会融资","2019","2019","更合镇"]
[null,11,"小洞“五好”新村居建设绿化提升项目工程","更合镇小洞村委会","休闲公园",0.2,0.7,"村集体地",15,"社会融资","2019","2019","更合镇"]
[null,12,"界村“五好”新村居建设绿化提升项目工程","更合镇界村村委会","休闲公园",0.7,0.2,"村集体地",10,"社会融资","2019","2019","更合镇"]
[null,13,"吉田“五好”新村居建设绿化提升项目工程","更合镇吉田村委会","休闲公园",0.18,0.08,"村集体地",10,"社会融资","2019","2019","更合镇"]
[null,14,"官山“五好”新村居建设绿化提升项目工程","更合镇官山村委会","休闲公园",0.14,0.6,"村集体地",15,"社会融资","2019","2019","更合镇"]
[null,15,"良村“五好”新村居建设绿化提升项目工程","更合镇良村村委会","休闲公园",0.13,0.7,"村集体地",10,"社会融资","2019","2019","更合镇"]
[null,16,"高村新农村建设绿化提升项目工程","更合镇高村村委会","休闲公园",0.4,0.1,"村集体地",40,"社会融资","2019","2019","更合镇"]
[null,17,"版村新农村建设绿化提升项目工程","更合镇版村村委会","休闲公园",0.1,0.05,"村集体地",10,"社会融资","2019","2019","更合镇"]
[null,18,"白石新农村建设绿化提升项目工程","更合镇白石村委会","休闲公园",0.14,0.05,"村集体地",10,"社会融资","2019","2019","更合镇"]
[null,19,"布练新农村建设绿化提升项目工程","更合镇布练村委会","休闲公园",0.13,0.04,"村集体地",10,"社会融资","2019","2019","更合镇"]
[null,20,"平塘新农村建设绿化提升项目工程","更合镇平塘村委会","休闲公园",0.33,0.2,"村集体地",40,"社会融资","2019","2019","更合镇"]
[null,21,"歌乐新农村建设绿化提升项目工程","更合镇歌乐村委会","休闲公园",0.2,0.1,"村集体地",20,"社会融资","2019","2019","更合镇"]
[null,22,"合居建设绿化提升项目工程","更合镇合水居委会","休闲公园",0.07,0.03,"村集体地",10,"社会融资","2019","2019","更合镇"]
[null,23,"冲尾村村居公园","明东村委会冲尾村","休闲公园",0.2,0.12,"村集体地",30,"社会融资","2018.1",2018.12,"明城镇"]
[null,24,"严田村村居公园","崇步村委会严田村","休闲公园",0.1,0.03,"村集体地",17,"社会融资","2018.1","2018.12","明城镇"]
[null,25,"潭朗新村村居公园","潭朗村委会新村","休闲公园",0.13,0.05,"村集体地",20,"社会融资","2018.1","2018.12","明城镇"]
[null,26,"罗塘村村居公园","新岗村委会罗塘村","休闲公园",0.1,0.03,"村集体地",18,"社会融资","2019.1","2019.12","明城镇"]
[null,27,"旧村村居公园","苗迳村委会旧村","休闲公园",0.12,0.06,"村集体地",18,"社会融资","2018.1","2018.12","明城镇"]
[null,28,"深水村村居公园","罗稳村委会深水村","休闲公园",0.2,0.12,"村集体地",50,"社会融资","2018.1","2018.12","明城镇"]
[null,29,"水镇村村居公园","明西村委会水镇村","休闲公园",0.4,0.2,"村集体地","待定","社会融资","2018.1","2018.12","明城镇"]
[null,30,"七社村村居公园","明阳村委会七社村","休闲公园",0.1,0.04,"村集体地",20,"社会融资","2019.1","2019.12","明城镇"]
[null,31,"大简村村居公园","明南村委会大简村","休闲公园",0.27,0.17,"村集体地",30,"社会融资","2018.1","2018.12","明城镇"]
[null,32,"云勇村村居公园","光明村委会云勇村","休闲公园",0.4,0.22,"村集体地","待定","社会融资","2018.1","2018.12","明城镇"]
[null,33,"上石塘村村居公园","明北村委会上石塘村","休闲公园",0.1,0.04,"村集体地",20,"社会融资","2019.1","2019.12","明城镇"]
[null,34,"洞心村村居公园","社区洞心村","休闲公园",0.1,0.03,"村集体地",20,"社会融资","2019.1","2019.12","明城镇"]
[null,35,"清泰村（居）公园","清泰七组","“五好”新村居绿化、景观及配套设施建设",0.1,0.03,"村集体地",50,"社会融资",2018.1,2018.12,"杨和镇"]
[null,36,"圆岗村（居）公园","圆岗","“五好”新村居绿化、景观及配套设施建设",0.2,0.05,"村集体地",50,"社会融资",2018.1,2018.12,"杨和镇"]
[null,37,"豸岗村（居）公园","豸岗","森林家园绿化建设",0.2,0.1,"村集体地",3,"社会融资",2018.1,2018.12,"杨和镇"]
[null,38,"对川村（居）公园","对川","绿化、景观及配套设施建设",0.1,0.02,"村集体地",3,"社会融资",2018.1,2018.12,"杨和镇"]
[null,39,"岗水村（居）公园","岑水","“五好”新村居绿化、景观及配套设施建设",0.1,0.02,"村集体地",50,"社会融资",2018.1,2018.12,"杨和镇"]
[null,40,"人和村（居）公园","大楠","绿化、景观及配套设施建设",0.2,0.04,"村集体地",3,"社会融资",2018.1,2018.12,"杨和镇"]
[null,41,"河东村（居）公园","牛扣","森林家园绿化建设",0.1,0.03,"村集体地",3,"社会融资",2018.1,2018.12,"杨和镇"]
[null,42,"河西居委会社会主义核心价值观公园","丽堂新村","绿化、景观及配套设施建设",0.6,0.25,"村集体地",80,"社会融资",2017.8,2018.12,"杨和镇"]
[null,43,"沙水村委会社会主义核心价值观公园","洞口村","绿化、景观及配套设施建设",0.05,0.01,"村集体地",30,"社会融资",2018.1,2018.12,"杨和镇"]
[null,44,"石水村委会社会主义核心价值观公园","新安村","绿化、景观及配套设施建设",0.2,0.05,"村集体地",30,"社会融资",2018.1,2018.12,"杨和镇"]
[null,45,"仙村睡莲公园","双涌二组","种植睡莲",13.33,"/","待定",200,"待定","2018-04-01",2020,"荷城街道"]
[null,46,"塘南荷花公园","塘伙村","种植荷花",3.87,"/","待定",60,"待定","2018-02-01",2020,"荷城街道"]
[null,47,"江湾荷花公园","下陈村","种植荷花",3.33,"/","待定",41,"待定","2018-04-01",2020,"荷城街道"]
[null,48,"泰兴荷花公园","镇地岗村","种植荷花",1.33,"/","待定",50,"待定","2018-04-01",2020,"荷城街道"]
[null,49,"王臣荷花公园","下五一村","种植荷花",1,"/","待定",49,"待定","2018-04-01",2020,"荷城街道"]
[null,50,"江湾桃花公园","上湾村","种植桃花",0.67,"/","待定",41,"待定","2018-04-01",2020,"荷城街道"]
[null,51,"王臣荷花葡萄园","松江村","种植荷花和葡萄园",0.8,"/","待定",41,"待定","2018-04-01",2020,"荷城街道"]
[null,52,"南洲荷花公园","开庄二组","种植荷花",1.53,"/","待定",50,"待定","2018-04-01",2020,"荷城街道"]
[null,53,"江湾居委会公园","上湾村","休闲公园",4.7,0.03,"待定",5,"待定","2018-04-01",2020,"荷城街道"]
[null,54,"王臣村委会公园","松岗村","休闲公园",2.2,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,55,"南洲村委会公园","塘肚村","休闲公园",0.6,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,56,"王臣村委会公园","上五一村","休闲公园",0.5,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,57,"江湾居委会","下陈\n村","休闲公园",5,0.03,"待定",5.5,"待定","2018-04-01",2020,"荷城街道"]
[null,58,"照明居民委员会\n","石潭村","休闲公园",0.5,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,59,"照明居委会","榴村陆家村","休闲公园",0.35,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,60,"照明居委会","塘美村","休闲公园",0.3,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,61,"范洲村委会","坑边村","休闲公园",0.4,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,62,"江湾居委会","上陈等村","休闲公园",0.5,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,63,"孔堂村委会","下良村","休闲公园",0.3,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,64,"上秀丽村委会","阮埇村","休闲公园",0.5,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,65,"南洲村委会","石砚村","休闲公园",0.3,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,66,"江湾居委会","江根村","休闲公园",0.5,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,67,"南洲村委会","冼村","休闲公园",0.4,0.03,"待定",3,"待定","2018-03-01",2020,"荷城街道"]
[null,68,"石洲村委会","上三台村","休闲公园",0.3,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,69,"泰和村委会","石演村","休闲公园",0.4,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,70,"泰兴村委会","槎江李家村","休闲公园",0.5,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,71,"泰兴村委会","下古椰村","休闲公园",0.3,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
[null,72,"塘南村委会","塘伙村","休闲公园",0.5,0.03,"待定",3,"待定","2018-04-01",2020,"荷城街道"]
["2.革命老区乡村\n振兴",1,"革命老区乡村振兴","各镇街","乡村绿化",1300,1300,"待定","待定","区级统筹",2018,2020,"区农林渔业局（农村工作）"]
[null,"项目小计","高明区共73个项目",null,null,1353.64,1306.16,null,1507.5]